## Gantt
Board - Heber Grazing Study (by weeks)
|  |  | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jun-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Jul-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022 | Aug-2022
| Start | End | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30
none - Analysis |  |  | 9: none - Analysis
Canopy and Ground Cover Preprocessing(Canopy and Ground Cover Preprocessing) | 09-Jun-2022 | 09-Jun-2022 | 9: Canopy and Ground Cover Preprocessing (09-Jun-22 - 09-Jun-22)
Canopy and Ground Cover Analysis/Plotting(Canopy and Ground Cover Analysis/Plotting) | 14-Jun-2022 | 14-Jun-2022 | 14: Canopy and Ground Cover Analysis/Plotting (14-Jun-22 - 14-Jun-22)
Double-check Paired-Plot Analysis(Double-check Paired-Plot Analysis) | 16-Jun-2022 | 16-Jun-2022 | 16: Double-check Paired-Plot Analysis (16-Jun-22 - 16-Jun-22)
none - Conclusion |  |  | 9: none - Conclusion
Write Up- Methods(Write Up- Methods) | 21-Jun-2022 | 24-Jun-2022 | 21: Write Up- Methods (21-Jun-22 - 24-Jun-22); 22: Write Up- Methods (21-Jun-22 - 24-Jun-22); 23: Write Up- Methods (21-Jun-22 - 24-Jun-22); 24: Write Up- Methods (21-Jun-22 - 24-Jun-22)
Write Up- Results(Write Up- Results) | 24-Jun-2022 | 29-Jun-2022 | 24: Write Up- Results (24-Jun-22 - 29-Jun-22); 25: Write Up- Results (24-Jun-22 - 29-Jun-22); 26: Write Up- Results (24-Jun-22 - 29-Jun-22); 27: Write Up- Results (24-Jun-22 - 29-Jun-22); 28: Write Up- Results (24-Jun-22 - 29-Jun-22); 29: Write Up- Results (24-Jun-22 - 29-Jun-22)
Write Up- Discussion(Write Up- Discussion) | 29-Jun-2022 | 05-Jul-2022 | 29: Write Up- Discussion (29-Jun-22 - 05-Jul-22); 30: Write Up- Discussion (29-Jun-22 - 05-Jul-22); 1: Write Up- Discussion (29-Jun-22 - 05-Jul-22); 2: Write Up- Discussion (29-Jun-22 - 05-Jul-22); 3: Write Up- Discussion (29-Jun-22 - 05-Jul-22); 4: Write Up- Discussion (29-Jun-22 - 05-Jul-22); 5: Write Up- Discussion (29-Jun-22 - 05-Jul-22)
Write Up- Introduction(Write Up- Introduction) | 05-Jul-2022 | 11-Jul-2022 | 5: Write Up- Introduction (05-Jul-22 - 11-Jul-22); 6: Write Up- Introduction (05-Jul-22 - 11-Jul-22); 7: Write Up- Introduction (05-Jul-22 - 11-Jul-22); 8: Write Up- Introduction (05-Jul-22 - 11-Jul-22); 9: Write Up- Introduction (05-Jul-22 - 11-Jul-22); 10: Write Up- Introduction (05-Jul-22 - 11-Jul-22); 11: Write Up- Introduction (05-Jul-22 - 11-Jul-22)